## Sheet1
Project Name |  |  |  | CaDC drains and flooring repair
Project Location |  |  |  | Cambridge Developmental Ceneter
Project Number |  |  |  | DMR-170034 | R230008
Project Budget |  |  |  | 750000 |  |  | 2957179.66
[5 empty] | Original |  | Revised |  |  |  |  | Amount
[5 empty] | Estimated |  | Estimated |  | Actual |  | Previously | this
[5 empty] | Amounts | % | Amounts | % | Amounts | % | Released | Request
CONSTRUCTION CONTRACTS: | [10 empty] | 0
| General Contract | [5 empty] | 2398686
|  | Name: | Surgent Construction |  | 630880 |  |  |  | 630880 |  | 0 | 630880
Vendor ID:
PROFESSIONAL SERVICES:
| Associate Architect/Engineer |  |  |  | 39200 |  | 245521 |  | 39200 |  | 39200 | 0
|  | Name: | Kramer Engineers
Vendor ID:
Type of Service: Design & Construction Administration
ALLOWANCE FOR CHANGE
| Change Order Fees: |  |  | * | 0 |  | 0 |  | 0 |  | 0 | 0
| OFCC Fees |  |  |  | 5000 |  | 81690.58 |  | 7500 |  | 5000 | 2500
| Pre-Bid Expenses and Contingency |  |  |  | 3920 |  | 231282.08 |  | 3920 |  | 3920 | 63088
|  |  | TOTAL |  | 679000 |  | 2957179.66 |  | 681500 |  | 48120 | 696468
|  |  |  | * | in A&E contract
0